## README
IT Reporting — Master Ingestion Template
This is the master workbook contract for the TeacherActive IT Reporting pack. Keep worksheet names, row 3 headers and Excel table names exact so the app can ingest the file reliably.
Workbook purpose | Capture clean reporting inputs in one structured place so the reporting pack can be rendered consistently in Excel, React or exported visuals.
How to use | Populate only the INPUT_ tabs. Leave headers intact. Use the Validation_Lists tab values for drop-downs where provided.
Recommended cadence | Monthly for the main report, with rolling quarterly updates for roadmap and ad hoc updates for risks, renewals and major incidents.
Period handling | Use month-end or reporting-month values for operational metrics. Use quarter labels for roadmap items. Use exact dates for tickets, changes, renewals and milestones.
Design principle | This workbook is for ingestion, not presentation. Keep data clean, structured and source-aligned. Presentation logic should sit downstream.
This workbook version | Dummy data populated for design, prototyping and visual development. Replace with real values later.
Template Key | IT_EXEC_TEMPLATE_V4
Template Version | 4
Network metric handling | Overall Network KPI is derived from office rows in INPUT_Office_Network_Avail.
Portfolio Gantt handling | 12-week rolling Gantt is derived from INPUT_Gantt_Workstreams and INPUT_Gantt_Milestones.
INPUT_Security_Patching | Populate with one row per record.
INPUT_Assets_Lifecycle | Populate with one row per record.
INPUT_Change_Release | Populate with one row per record.
INPUT_Dev_Delivery | Populate with one row per record.
INPUT_Project_Portfolio | Populate with one row per record.
INPUT_Rolling_Roadmap | Populate with one row per record.
INPUT_Budget_Commercials | Populate with one row per record.
INPUT_Top_Risks | Populate with one row per record.
INPUT_Narrative_Notes | Populate with one row per record.
Master template status | This workbook is the current master ingestion template for the IT Reporting pack. Use it for all new monthly packs unless a newer template version is formally issued.
Workbook authority | The app expects the exact worksheet names, row 3 headers and Excel table names defined in this workbook. Do not rename sheets, move the header row, or remove tables.
Input tab rule | Populate INPUT_ tabs and Periods only. Reporting_Framework, Metric_Catalogue and Validation_Lists are reference tabs.
Exec Summary handling | Exec Summary is authored in the app, not in Excel. The workbook remains the source of truth for structured reporting data.
Map handling | Office map plotting uses app-owned coordinates. Office_Locations Map X and Map Y remain reference fields and are not the live plotting source.
Chart settings handling | Chart overlays are controlled in INPUT_Chart_Settings.
Required input sheets | Periods, INPUT_Office_Network_Avail, INPUT_Service_Availability, INPUT_Support_Operations, INPUT_Top_Oldest_Tickets, INPUT_Security_Patching, INPUT_Assets_Lifecycle, INPUT_Change_Release, INPUT_Dev_Delivery, INPUT_Project_Portfolio, INPUT_Rolling_Roadmap, INPUT_Gantt_Workstreams, INPUT_Gantt_Milestones, INPUT_Budget_Commercials, INPUT_Top_Risks, INPUT_Narrative_Notes, INPUT_Chart_Settings.
Required table names | TOfficeLocations, TOfficeNetworkAvailability, TServiceAvailability, TSupportOperations, TTopOldestTickets, TSecurityPatching, TAssetsLifecycle, TChangeRelease, TDevDelivery, TProjectPortfolio, TRollingRoadmap, TPortfolioGanttWorkstreams, TPortfolioGanttMilestones, TBudgetCommercials, TTopRisks, TNarrativeNotes, TChartSettings.
Periods sheet rule | Periods must contain Report Cut-Off Date on row 3 and exactly one current period marked Yes.

## Reporting_Framework
Exec IT Reporting Framework
This is the agreed reporting scope for the monthly exec pack.
Page / Section | Purpose | Core exec question | Suggested visuals | Primary source domains
1. Executive technology scorecard | High-level monthly summary | Are we broadly in control? | Status summary, KPI tiles, wins/concerns, decisions | All domains
2. Service availability and resilience | Reliability of core services | Can the business rely on our services? | Availability tiles, outage trend, status summary | Service availability, incidents, backups
3. Support operations and user experience | Support performance and user sentiment | Are users getting a good service? | KPI cards, trend, category bars, ageing, top oldest tickets, ticket CSAT | Support ops, ticket CSAT
4. Security, patching and compliance | Security posture and control health | Are we secure and inside policy? | Compliance tiles, severity trend, remediation table | Security, patching, vulnerabilities
5. Estate, assets and lifecycle | Lifecycle and hardware control | Are we managing the estate responsibly? | Age profile, stock cards, lifecycle split | Assets, stock, refresh
6. Change, release and platform operations | Operational control over change | Are we changing safely? | Change mix, success rate, release stats | Change and release
7. Delivery, projects and rolling roadmap | Execution and forward plan | Are we delivering meaningful change? | Delivery KPIs, project RAG, roadmap by quarter, project CSAT | Dev, projects, roadmap
8. Budget, commercials and supplier position | Financial and supplier oversight | Are we spending well and where is pressure building? | Budget vs actual, trend, renewals, savings | Budget, cloud/licensing, vendors
9. Top risks, issues and decisions | Escalation and governance | What needs attention or decisions? | Risk table, impact/likelihood heat cues | Risks, issues, decisions

## Metric_Catalogue
Metric Catalogue
Use this as the master list of what the exec pack is expected to report.
Domain | Metric | Definition | Preferred grain | Primary visual | Notes
Service availability | Network availability % | Availability of network services in the reporting month | Monthly | Availability tile | Could include WAN if split separately
Service availability | Cloud availability % | Availability of named cloud platform or service | Monthly by service | Availability tile | AWS, Azure, Private Cloud etc
Service availability | Critical business app availability % | Availability of named critical application | Monthly by app | Availability tile / table | Use only truly critical apps
Service availability | Outage minutes | Total user-impacting outage minutes | Monthly | Trend / callout | User-impacting only
Support | Tickets opened | Support tickets created in period | Monthly | KPI / trend
Support | Tickets closed | Support tickets closed in period | Monthly | KPI / trend
Support | Backlog at month end | Open tickets at period end | Monthly | KPI / trend
Support | Average age of open tickets | Average age in days of currently open tickets | Monthly snapshot | KPI
Support | Average resolution time | Average ticket resolution time in days | Monthly | KPI
Support | Resolution SLA % | Share resolved within SLA | Monthly | KPI
Support | First response SLA % | Share responded to within SLA | Monthly | KPI
Support | Reopen rate % | Share of tickets reopened | Monthly | KPI
Support | Ticket CSAT | Customer satisfaction score for support tickets | Monthly | KPI / trend | Include response rate too
Support | Top 10 oldest tickets | Oldest currently open tickets | Monthly snapshot | Table
Security | Workstation patch compliance % | Share of workstations compliant with patch policy | Monthly | KPI / trend
Security | Server patch compliance % | Share of servers compliant with patch policy | Monthly | KPI / trend
Security | Critical patch compliance % | Share of critical patches applied within policy window | Monthly | KPI / trend
Security | Vulnerability counts by severity | Open vulnerability counts by severity | Monthly | Stacked severity visual | Critical, High, Medium, Low
Security | Security incidents | Number of security incidents in period | Monthly | KPI / trend
Assets | Average age of devices | Average age of active devices in months | Monthly | KPI / profile
Assets | Stock levels | Devices held in stock by type | Monthly snapshot | KPI cards / table
Assets | Refresh spend | Spend on asset refresh in period | Monthly | Budget visual
Change | Total changes | All changes raised in period | Monthly | KPI
Change | Emergency changes | Emergency changes raised in period | Monthly | KPI
Change | Failed changes % | Share of failed changes | Monthly | KPI / trend
Development | Dev tasks opened | Development tasks created in period | Monthly | KPI / trend
Development | Dev tasks closed | Development tasks completed in period | Monthly | KPI / trend
Development | Dev backlog | Open development tasks at period end | Monthly | KPI / trend
Projects | Project CSAT | Satisfaction for completed/in-flight project delivery | Monthly or quarterly | KPI / trend | Could be sponsor satisfaction
Projects | Active projects | Projects in flight | Monthly | KPI / table
Projects | Project RAG | Current project status | Monthly by project | RAG table
Roadmap | Rolling roadmap items | Planned initiatives by quarter and lane | Quarterly | Roadmap visual | Rolling 4 quarters
Budget | Budget vs actual | Budget compared to actual cost by line | Monthly | Variance visual / table
Budget | Cloud/licensing trend | Trend of cloud and licensing spend | Monthly | Trend
Budget | Savings achieved | Savings or cost avoidance achieved | Monthly | KPI / commentary
Budget | Avoidable cost risk | Known cost exposure that can be mitigated | Monthly | KPI / commentary
Budget | Vendor renewals upcoming | Upcoming renewals requiring decisions | Monthly | Renewals table
Risks | Top risks | Key operational, security, delivery or commercial risks | Monthly snapshot | Risk table | Include impact and likelihood

## Validation_Lists
Status_RAG | Risk_Impact | Risk_Likelihood | Priority | Roadmap_Lane | Roadmap_Quarter | Budget_Line | Asset_Type | Change_Type | Change_Result | Ticket_Category | Project_Status
Green | Low | Rare | Low | Core IT operations | 2026 Q1 | Cloud services | Laptop | Standard | Successful | Email | Not started
Amber | Medium | Unlikely | Medium | Security & compliance | 2026 Q2 | Licensing | Desktop | Normal | Successful with issue | Permissions | On track
Red | High | Possible | High | Infrastructure & cloud | 2026 Q3 | Connectivity | Mobile | Emergency | Failed | Hardware | At risk
| Critical | Likely | Critical | End-user computing | 2026 Q4 | Managed services | Tablet |  | Rolled back | Software | Delayed
|  | Almost Certain |  | Applications & data | 2027 Q1 | Hardware / refresh | Monitor |  |  | Network | Completed
|  |  |  | Product / development | 2027 Q2 | Security tooling | Server |  |  | Telephony | On hold
|  |  |  | Business transformation | 2027 Q3 | Professional services | Network device |  |  | Data request | Cancelled
[5 empty] | 2027 Q4 | Other | Peripheral |  |  | Training
[7 empty] | Other |  |  | Security
Other

## Periods
Reporting Periods
One row per reporting month. Mark exactly one row as the current period and provide the stored report cut-off date.
Reporting Month | Month End Date | Quarter | Financial Year | Is Current Period | Report Cut-Off Date
2026-01 | 2026-01-31 | 2026 Q1 | FY2025/26 | No | 2026-01-19
2026-02 | 2026-02-28 | 2026 Q1 | FY2025/26 | No | 2026-02-19
2026-03 | 2026-03-31 | 2026 Q1 | FY2025/26 | No | 2026-03-19
2026-04 | 2026-04-30 | 2026 Q2 | FY2026/27 | No | 2026-04-19
2026-05 | 2026-05-31 | 2026 Q2 | FY2026/27 | No | 2026-05-19
2026-06 | 2026-06-30 | 2026 Q2 | FY2026/27 | Yes | 2026-06-19

## Entities
Entities
Reference list for services, platforms and domains in scope for the exec pack.
Entity Type | Entity Name | Grouping | In Scope | Notes
Service | Network | Core services | Yes | Corporate network and connectivity
Service | AWS | Cloud platforms | Yes | Core workloads and integrations
Service | Azure | Cloud platforms | Yes | Identity and Microsoft estate
Service | Private Cloud | Cloud platforms | Yes | Legacy hosted estate
Application | TABS / TAMS | Critical applications | Yes | Core business platform
Application | Microsoft 365 | Critical applications | Yes | Collaboration and productivity
Application | Website / SharePoint | Business applications | Yes | External and internal content
Application | Telephony | Business applications | Yes | Voice and contact channels
Supplier | Microsoft | Strategic suppliers | Yes
Supplier | AWS | Strategic suppliers | Yes
Supplier | HP | Strategic suppliers | Yes

## Office_Locations
Office Locations
In-scope UK offices used for the network map and office-availability view.
Office Name | Region | In Scope | Display Order | Map X | Map Y
Birmingham | Midlands | Yes | 1 | 238 | 255
Manchester | North West | Yes | 2 | 196 | 195
Leeds | Yorkshire | Yes | 3 | 228 | 185
London City | London | Yes | 4 | 298 | 355
London East | London | Yes | 5 | 308 | 360
Bristol | South West | Yes | 6 | 148 | 375
Sheffield | Yorkshire | Yes | 7 | 228 | 198
Nottingham | East Midlands | Yes | 8 | 242 | 232
Leicester | East Midlands | Yes | 9 | 244 | 248
Cardiff | Wales | Yes | 10 | 128 | 378
Swansea | Wales | Yes | 11 | 102 | 370
Liverpool | North West | Yes | 12 | 182 | 208
Newcastle | North East | Yes | 13 | 228 | 108
Derby | East Midlands | Yes | 14 | 238 | 238
Coventry | Midlands | Yes | 15 | 248 | 262
Worcester | Midlands | Yes | 16 | 218 | 272
Oxford | South East | Yes | 17 | 248 | 308
Cambridge | East | Yes | 18 | 292 | 295
Southampton | South | Yes | 19 | 228 | 398
Plymouth | South West | Yes | 20 | 105 | 455
Norwich | East | Yes | 21 | 328 | 295
Exeter | South West | Yes | 22 | 128 | 448

## INPUT_Office_Network_Avail
INPUT Office Network Availability
One row per office per reporting month. Overall Network KPI is derived from this sheet.
Reporting Month | Office Name | Availability % | Outage Minutes | Major Incidents | Commentary
2026-01 | Birmingham | 99.92% | 36 | 0 | Minor transient disruption.
2026-01 | Manchester | 99.88% | 54 | 0 | Monitored connectivity issue.
2026-01 | Leeds | 99.75% | 112 | 0 | Monitored connectivity issue.
2026-01 | London City | 99.95% | 22 | 0 | Minor transient disruption.
2026-01 | London East | 99.90% | 45 | 0 | Minor transient disruption.
2026-01 | Bristol | 99.85% | 67 | 0 | Monitored connectivity issue.
2026-01 | Sheffield | 99.70% | 134 | 0 | Monitored connectivity issue.
2026-01 | Nottingham | 99.80% | 89 | 0 | Monitored connectivity issue.
2026-01 | Leicester | 99.88% | 54 | 0 | Monitored connectivity issue.
2026-01 | Cardiff | 97.80% | 982 | 1 | User-impacting outage recorded.
2026-01 | Swansea | 98.10% | 848 | 1 | User-impacting outage recorded.
2026-01 | Liverpool | 99.82% | 80 | 0 | Monitored connectivity issue.
2026-01 | Newcastle | 99.78% | 98 | 0 | Monitored connectivity issue.
2026-01 | Derby | 99.83% | 76 | 0 | Monitored connectivity issue.
2026-01 | Coventry | 99.87% | 58 | 0 | Monitored connectivity issue.
2026-01 | Worcester | 99.91% | 40 | 0 | Minor transient disruption.
2026-01 | Oxford | 99.93% | 31 | 0 | Minor transient disruption.
2026-01 | Cambridge | 99.89% | 49 | 0 | Monitored connectivity issue.
2026-01 | Southampton | 99.85% | 67 | 0 | Monitored connectivity issue.
2026-01 | Plymouth | 99.76% | 107 | 0 | Monitored connectivity issue.
2026-01 | Norwich | 99.80% | 89 | 0 | Monitored connectivity issue.
2026-01 | Exeter | 99.81% | 85 | 0 | Monitored connectivity issue.
2026-02 | Birmingham | 99.95% | 20 | 0 | Minor transient disruption.
2026-02 | Manchester | 99.93% | 28 | 0 | Minor transient disruption.
2026-02 | Leeds | 99.80% | 81 | 0 | Monitored connectivity issue.
2026-02 | London City | 99.97% | 12 | 0 | Minor transient disruption.
2026-02 | London East | 99.93% | 28 | 0 | Minor transient disruption.
2026-02 | Bristol | 99.90% | 40 | 0 | Minor transient disruption.
2026-02 | Sheffield | 99.78% | 89 | 0 | Monitored connectivity issue.
2026-02 | Nottingham | 99.85% | 60 | 0 | Monitored connectivity issue.
2026-02 | Leicester | 99.91% | 36 | 0 | Minor transient disruption.
2026-02 | Cardiff | 98.50% | 605 | 1 | User-impacting outage recorded.
2026-02 | Swansea | 98.60% | 564 | 1 | User-impacting outage recorded.
2026-02 | Liverpool | 99.88% | 48 | 0 | Monitored connectivity issue.
2026-02 | Newcastle | 99.84% | 65 | 0 | Monitored connectivity issue.
2026-02 | Derby | 99.89% | 44 | 0 | Monitored connectivity issue.
2026-02 | Coventry | 99.91% | 36 | 0 | Minor transient disruption.
2026-02 | Worcester | 99.94% | 24 | 0 | Minor transient disruption.
2026-02 | Oxford | 99.96% | 16 | 0 | Minor transient disruption.
2026-02 | Cambridge | 99.93% | 28 | 0 | Minor transient disruption.
2026-02 | Southampton | 99.89% | 44 | 0 | Monitored connectivity issue.
2026-02 | Plymouth | 99.82% | 73 | 0 | Monitored connectivity issue.
2026-02 | Norwich | 99.86% | 56 | 0 | Monitored connectivity issue.
2026-02 | Exeter | 99.87% | 52 | 0 | Monitored connectivity issue.
2026-03 | Birmingham | 100.00% | 0 | 0 | No incidents.
2026-03 | Manchester | 99.97% | 13 | 0 | Minor transient disruption.
2026-03 | Leeds | 99.90% | 45 | 0 | Minor transient disruption.
2026-03 | London City | 100.00% | 0 | 0 | No incidents.
2026-03 | London East | 99.96% | 18 | 0 | Minor transient disruption.
2026-03 | Bristol | 99.93% | 31 | 0 | Minor transient disruption.
2026-03 | Sheffield | 99.88% | 54 | 0 | Monitored connectivity issue.
2026-03 | Nottingham | 99.92% | 36 | 0 | Minor transient disruption.
2026-03 | Leicester | 99.95% | 22 | 0 | Minor transient disruption.
2026-03 | Cardiff | 99.20% | 357 | 0 | Monitored connectivity issue.
2026-03 | Swansea | 99.10% | 402 | 0 | Monitored connectivity issue.
2026-03 | Liverpool | 99.93% | 31 | 0 | Minor transient disruption.
2026-03 | Newcastle | 99.91% | 40 | 0 | Minor transient disruption.
2026-03 | Derby | 99.94% | 27 | 0 | Minor transient disruption.
2026-03 | Coventry | 99.96% | 18 | 0 | Minor transient disruption.
2026-03 | Worcester | 99.97% | 13 | 0 | Minor transient disruption.
2026-03 | Oxford | 99.98% | 9 | 0 | Minor transient disruption.
2026-03 | Cambridge | 99.96% | 18 | 0 | Minor transient disruption.
2026-03 | Southampton | 99.94% | 27 | 0 | Minor transient disruption.
2026-03 | Plymouth | 99.89% | 49 | 0 | Monitored connectivity issue.
2026-03 | Norwich | 99.92% | 36 | 0 | Minor transient disruption.
2026-03 | Exeter | 99.92% | 36 | 0 | Minor transient disruption.
2026-04 | Birmingham | 100.00% | 0 | 0 | No incidents.
2026-04 | Manchester | 100.00% | 0 | 0 | No incidents.
2026-04 | Leeds | 99.95% | 22 | 0 | Minor transient disruption.
2026-04 | London City | 100.00% | 0 | 0 | No incidents.
2026-04 | London East | 99.98% | 9 | 0 | Minor transient disruption.
2026-04 | Bristol | 99.97% | 13 | 0 | Minor transient disruption.
2026-04 | Sheffield | 99.92% | 35 | 0 | Minor transient disruption.
2026-04 | Nottingham | 99.96% | 17 | 0 | Minor transient disruption.
2026-04 | Leicester | 99.98% | 9 | 0 | Minor transient disruption.
2026-04 | Cardiff | 99.42% | 251 | 0 | Monitored connectivity issue.
2026-04 | Swansea | 99.40% | 259 | 0 | Monitored connectivity issue.
2026-04 | Liverpool | 99.97% | 13 | 0 | Minor transient disruption.
2026-04 | Newcastle | 99.95% | 22 | 0 | Minor transient disruption.
2026-04 | Derby | 99.97% | 13 | 0 | Minor transient disruption.
2026-04 | Coventry | 99.98% | 9 | 0 | Minor transient disruption.
2026-04 | Worcester | 99.99% | 4 | 0 | Minor transient disruption.
2026-04 | Oxford | 100.00% | 0 | 0 | No incidents.
2026-04 | Cambridge | 99.99% | 4 | 0 | Minor transient disruption.
2026-04 | Southampton | 99.97% | 13 | 0 | Minor transient disruption.
2026-04 | Plymouth | 99.94% | 26 | 0 | Minor transient disruption.
2026-04 | Norwich | 99.96% | 17 | 0 | Minor transient disruption.
2026-04 | Exeter | 99.96% | 17 | 0 | Minor transient disruption.
2026-05 | Birmingham | 99.98% | 9 | 0 | Minor transient disruption.
2026-05 | Manchester | 100.00% | 0 | 0 | No incidents.
2026-05 | Leeds | 99.98% | 9 | 0 | Minor transient disruption.
2026-05 | London City | 100.00% | 0 | 0 | No incidents.
2026-05 | London East | 100.00% | 0 | 0 | No incidents.
2026-05 | Bristol | 100.00% | 0 | 0 | No incidents.
2026-05 | Sheffield | 99.96% | 18 | 0 | Minor transient disruption.
2026-05 | Nottingham | 99.99% | 4 | 0 | Minor transient disruption.
2026-05 | Leicester | 100.00% | 0 | 0 | No incidents.
2026-05 | Cardiff | 99.55% | 201 | 0 | Monitored connectivity issue.
2026-05 | Swansea | 99.58% | 187 | 0 | Monitored connectivity issue.
2026-05 | Liverpool | 100.00% | 0 | 0 | No incidents.
2026-05 | Newcastle | 99.98% | 9 | 0 | Minor transient disruption.
2026-05 | Derby | 99.99% | 4 | 0 | Minor transient disruption.
2026-05 | Coventry | 100.00% | 0 | 0 | No incidents.
2026-05 | Worcester | 100.00% | 0 | 0 | No incidents.
2026-05 | Oxford | 100.00% | 0 | 0 | No incidents.
2026-05 | Cambridge | 100.00% | 0 | 0 | No incidents.
2026-05 | Southampton | 100.00% | 0 | 0 | No incidents.
2026-05 | Plymouth | 99.97% | 13 | 0 | Minor transient disruption.
2026-05 | Norwich | 99.98% | 9 | 0 | Minor transient disruption.
2026-05 | Exeter | 99.99% | 4 | 0 | Minor transient disruption.
2026-06 | Birmingham | 100.00% | 0 | 0 | No incidents.
2026-06 | Manchester | 100.00% | 0 | 0 | No incidents.
2026-06 | Leeds | 100.00% | 0 | 0 | No incidents.
2026-06 | London City | 100.00% | 0 | 0 | No incidents.
2026-06 | London East | 100.00% | 0 | 0 | No incidents.
2026-06 | Bristol | 100.00% | 0 | 0 | No incidents.
2026-06 | Sheffield | 99.98% | 9 | 0 | Minor transient disruption.
2026-06 | Nottingham | 100.00% | 0 | 0 | No incidents.
2026-06 | Leicester | 100.00% | 0 | 0 | No incidents.
2026-06 | Cardiff | 99.62% | 164 | 0 | Monitored connectivity issue.
2026-06 | Swansea | 99.70% | 130 | 0 | Monitored connectivity issue.
2026-06 | Liverpool | 100.00% | 0 | 0 | No incidents.
2026-06 | Newcastle | 100.00% | 0 | 0 | No incidents.
2026-06 | Derby | 100.00% | 0 | 0 | No incidents.
2026-06 | Coventry | 100.00% | 0 | 0 | No incidents.
2026-06 | Worcester | 100.00% | 0 | 0 | No incidents.
2026-06 | Oxford | 100.00% | 0 | 0 | No incidents.
2026-06 | Cambridge | 100.00% | 0 | 0 | No incidents.
2026-06 | Southampton | 100.00% | 0 | 0 | No incidents.
2026-06 | Plymouth | 100.00% | 0 | 0 | No incidents.
2026-06 | Norwich | 100.00% | 0 | 0 | No incidents.
2026-06 | Exeter | 100.00% | 0 | 0 | No incidents.

## INPUT_Service_Availability
INPUT Service Availability
One row per service per reporting month.
Reporting Month | Service Name | Service Type | Availability % | Target % | Outage Minutes | Major Incidents | Backup Success % | Restore Test Status | Commentary
2026-01 | AWS | Cloud | 99.98% | 99.90% | 9 | 0 |  |  | No material outage.
2026-01 | Azure | Cloud | 99.99% | 99.90% | 4 | 0 |  |  | Identity services stable.
2026-01 | Private Cloud | Cloud | 97.80% | 99.50% | 982 | 1 | 97.9% | Fail | Legacy platform outage impacted hosted services.
2026-01 | TABS / TAMS | Critical Application | 99.70% | 99.50% | 134 | 1 |  |  | Impact linked to private cloud incident.
2026-01 | Microsoft 365 | Critical Application | 99.99% | 99.90% | 5 | 0
2026-02 | AWS | Cloud | 99.99% | 99.90% | 7 | 0
2026-02 | Azure | Cloud | 100.0% | 99.90% | 0 | 0
2026-02 | Private Cloud | Cloud | 98.00% | 99.50% | 864 | 1 | 98.5% | Fail | Single platform outage affected hosted service.
2026-02 | TABS / TAMS | Critical Application | 99.74% | 99.50% | 112 | 0 |  |  | Recovered after platform remediation.
2026-02 | Microsoft 365 | Critical Application | 99.98% | 99.90% | 9 | 0
2026-03 | AWS | Cloud | 99.99% | 99.90% | 6 | 0
2026-03 | Azure | Cloud | 100.0% | 99.90% | 0 | 0
2026-03 | Private Cloud | Cloud | 99.10% | 99.50% | 402 | 0 | 99.0% | Pass | Stability improved after February fix.
2026-03 | TABS / TAMS | Critical Application | 99.88% | 99.50% | 38 | 0 |  |  | Improved underlying hosting stability.
2026-03 | Microsoft 365 | Critical Application | 99.99% | 99.90% | 3 | 0
2026-04 | AWS | Cloud | 99.99% | 99.90% | 5 | 0
2026-04 | Azure | Cloud | 99.99% | 99.90% | 2 | 0
2026-04 | Private Cloud | Cloud | 99.40% | 99.50% | 261 | 0 | 99.4% | Pass | Now within expected tolerance.
2026-04 | TABS / TAMS | Critical Application | 99.92% | 99.50% | 24 | 0
2026-04 | Microsoft 365 | Critical Application | 99.99% | 99.90% | 3 | 0
2026-05 | AWS | Cloud | 100.0% | 99.90% | 0 | 0
2026-05 | Azure | Cloud | 99.99% | 99.90% | 2 | 0
2026-05 | Private Cloud | Cloud | 99.55% | 99.50% | 131 | 0 | 99.6% | Pass | Legacy estate now stable but still monitored.
2026-05 | TABS / TAMS | Critical Application | 99.95% | 99.50% | 12 | 0
2026-05 | Microsoft 365 | Critical Application | 99.99% | 99.90% | 2 | 0
2026-06 | AWS | Cloud | 100.0% | 99.90% | 0 | 0
2026-06 | Azure | Cloud | 100.0% | 99.90% | 0 | 0
2026-06 | Private Cloud | Cloud | 99.62% | 99.50% | 98 | 0 | 99.8% | Pass | Residual issues remain low.
2026-06 | TABS / TAMS | Critical Application | 99.97% | 99.50% | 8 | 0
2026-06 | Microsoft 365 | Critical Application | 100.0% | 99.90% | 0 | 0

## INPUT_Support_Operations
INPUT Support Operations
One row per reporting month. Use this for monthly support KPIs and user experience metrics.
Reporting Month | Tickets Opened | Tickets Closed | Backlog End | Average Age Open Days | Average Resolution Days | First Response SLA % | Resolution SLA % | Reopen Rate % | Major Incidents | Ticket CSAT | CSAT Response Rate % | Top Category | Commentary
2026-01 | 1080 | 1082 | 39 | 4.4 | 1.6 | 98.0% | 98.5% | 2.3% | 0 | 4.6/5 | 17.0% | Email Related | January carry-over remained controlled despite elevated intake.
2026-02 | 949 | 957 | 31 | 4.2 | 1.5 | 98.1% | 98.7% | 2.1% | 0 | 4.7/5 | 18.0% | Email Related | Volumes returned to expected seasonal levels.
2026-03 | 1015 | 1004 | 42 | 4.5 | 1.6 | 97.8% | 98.2% | 2.2% | 1 | 4.5/5 | 16.0% | Permissions | One incident month but service metrics remained within tolerance.
2026-04 | 923 | 948 | 17 | 3.8 | 1.3 | 98.6% | 99.0% | 1.9% | 0 | 4.8/5 | 19.0% | Email Related | Backlog reduced materially after workflow tidy-up.
2026-05 | 978 | 962 | 33 | 4 | 1.4 | 98.3% | 98.8% | 2.0% | 0 | 4.7/5 | 17.5% | New User Setup | Seasonal onboarding volumes increased but service stayed strong.
2026-06 | 1008 | 1016 | 25 | 3.6 | 1.2 | 98.9% | 99.1% | 1.8% | 0 | 4.8/5 | 20.0% | Email Related | Best combined service and CSAT month in the period.

## INPUT_Top_Oldest_Tickets
INPUT Top Oldest Tickets
One row per open ticket. Keep this tab to the 10 oldest currently open tickets only.
Reporting Month | Ticket ID | Title | Category | Owner / Queue | Current Status | Age Days | Business Critical? | Blocker / Reason Still Open | Target Resolution Date | Next Action
2026-06 | INC-003871 | Laptop replacement for branch manager | Hardware | Service Desk | In Progress | 67 | Yes | Awaiting device arrival from supplier | 2026-07-08 | Escalate expedited shipment with HP
2026-06 | INC-003844 | Historic mailbox permission mismatch | Permissions | Applications | In Progress | 59 | No | Requires joint M365 and app review | 2026-07-05 | Complete technical review and test
2026-06 | INC-003811 | Private cloud report export failure | Software | Applications | Pending Change | 54 | Yes | Change window required | 2026-07-03 | Implement approved fix in next window
2026-06 | INC-003799 | Telephony handsets intermittent in Cardiff | Telephony | Infrastructure | In Progress | 49 | No | Carrier diagnostics outstanding | 2026-07-01 | Obtain carrier trace results
2026-06 | INC-003772 | Shared mailbox delivery delay | Email | Service Desk | Monitoring | 45 | No | Issue intermittent; monitoring in place | 2026-06-30 | Review message trace outcomes
2026-06 | INC-003741 | Network printer authentication loop | Hardware | Service Desk | In Progress | 41 | No | Firmware compatibility check needed | 2026-06-28 | Apply firmware patch and retest
2026-06 | INC-003735 | Candidate attachment size failure | Software | Applications | In Progress | 39 | No | Vendor support ticket open | 2026-06-27 | Chase vendor response
2026-06 | INC-003726 | Permissions sync mismatch for finance users | Permissions | Applications | In Progress | 36 | Yes | Dependent on identity sync change | 2026-06-26 | Complete dependency change
2026-06 | INC-003714 | Meeting room panel offline | Hardware | Service Desk | Awaiting Parts | 34 | No | Replacement panel on order | 2026-06-25 | Fit replacement panel
2026-06 | INC-003703 | Data extract delayed for payroll audit | Data request | Service Desk | In Progress | 32 | Yes | Awaiting business confirmation of fields | 2026-06-24 | Confirm final field list with payroll

## INPUT_Security_Patching
INPUT Security Patching
One row per reporting month. Use percentages for compliance measures and counts for severity volumes.
Reporting Month | Workstation Patch Compliance % | Server Patch Compliance % | Critical Patch Compliance % | Devices Outside Policy | Critical Vulns | High Vulns | Medium Vulns | Low Vulns | Security Incidents | MFA Coverage % | Endpoint Coverage % | Overdue Remediation Items | Commentary
2026-01 | 92.8% | 95.2% | 89.4% | 53 | 4 | 91 | 49 | 3 | 0 | 98.7% | 99.9% | 15 | Private cloud issue increased remediation queue.
2026-02 | 93.5% | 96.0% | 91.0% | 42 | 2 | 86 | 34 | 3 | 0 | 99.0% | 100.0% | 11 | Critical patching within tolerance but remediation queue still elevated.
2026-03 | 94.4% | 96.8% | 92.2% | 37 | 2 | 78 | 31 | 2 | 1 | 99.1% | 100.0% | 10 | One security incident closed without material impact.
2026-04 | 95.8% | 97.1% | 94.0% | 29 | 1 | 64 | 27 | 2 | 0 | 99.2% | 100.0% | 8 | Patching trend improving month on month.
2026-05 | 96.3% | 97.6% | 95.1% | 24 | 1 | 58 | 24 | 2 | 0 | 99.4% | 100.0% | 7 | Estate moving towards target state.
2026-06 | 97.1% | 98.0% | 96.5% | 18 | 0 | 49 | 19 | 2 | 0 | 99.5% | 100.0% | 5 | Best compliance month in period; no critical backlog.

## INPUT_Assets_Lifecycle
INPUT Assets Lifecycle
One row per reporting month and asset grouping if needed.
Reporting Month | Asset Type | Active Devices | Average Age Months | % Within Lifecycle | % Out of Lifecycle | Stock On Hand | Months Stock Cover | Awaiting Deployment | Awaiting Disposal | Refresh Spend | Incidents Linked to Aged Kit | Commentary
2026-01 | Laptop | 418 | 32.8 | 76.0% | 24.0% | 28 | 1.4 | 11 | 10 | 14200 | 17 | Refresh had started but ageing cohort remained large.
2026-01 | Mobile | 266 | 22.5 | 90.0% | 10.0% | 14 | 1.8 | 4 | 6 | 0 | 2
2026-01 | Monitor | 455 | 38.2 | 71.0% | 29.0% | 26 | 3.2 | 2 | 8 | 0 | 5 | Monitor estate ageing but lower support impact than laptops.
2026-02 | Laptop | 412 | 31.4 | 78.0% | 22.0% | 34 | 1.8 | 7 | 12 | 18500 | 14 | Refresh progressing but ageing cohort still visible.
2026-02 | Mobile | 268 | 22.1 | 91.0% | 9.0% | 16 | 2.1 | 3 | 5 | 0 | 2
2026-02 | Monitor | 454 | 37.9 | 72.0% | 28.0% | 24 | 3 | 2 | 8 | 0 | 4
2026-03 | Laptop | 409 | 30.6 | 80.0% | 20.0% | 29 | 1.5 | 8 | 14 | 12400 | 12 | Refresh wave 2 started to reduce aged estate.
2026-03 | Mobile | 269 | 21.8 | 92.0% | 8.0% | 18 | 2.3 | 2 | 5 | 0 | 2
2026-03 | Monitor | 454 | 37.5 | 73.0% | 27.0% | 23 | 2.8 | 1 | 9 | 0 | 4
2026-04 | Laptop | 406 | 29.9 | 82.0% | 18.0% | 31 | 1.6 | 6 | 10 | 15600 | 10 | Incident drag from old devices is reducing.
2026-04 | Mobile | 270 | 21.2 | 93.0% | 7.0% | 17 | 2.2 | 2 | 4 | 0 | 1
2026-04 | Monitor | 453 | 37 | 74.0% | 26.0% | 22 | 2.7 | 1 | 7 | 0 | 4
2026-05 | Laptop | 404 | 29.1 | 84.0% | 16.0% | 35 | 1.8 | 5 | 8 | 9200 | 8 | Stock position healthy ahead of Q3 refresh.
2026-05 | Mobile | 270 | 20.9 | 94.0% | 6.0% | 18 | 2.4 | 2 | 4 | 0 | 1
2026-05 | Monitor | 452 | 36.7 | 75.0% | 25.0% | 21 | 2.6 | 1 | 7 | 0 | 3
2026-06 | Laptop | 401 | 28.3 | 86.0% | 14.0% | 38 | 2 | 4 | 6 | 11800 | 7 | Strongest lifecycle position in the half-year.
2026-06 | Mobile | 271 | 20.4 | 95.0% | 5.0% | 19 | 2.5 | 1 | 3 | 0 | 1
2026-06 | Monitor | 451 | 36.3 | 76.0% | 24.0% | 20 | 2.5 | 1 | 6 | 0 | 3

## INPUT_Change_Release
INPUT Change Release
One row per reporting month.
Reporting Month | Total Changes | Standard Changes | Normal Changes | Emergency Changes | Successful Changes | Failed Changes | Rolled Back Changes | Change Success Rate % | Changes Causing Incidents | Releases Deployed | Planned Maintenance Completed | Commentary
2026-01 | 48 | 20 | 22 | 6 | 44 | 3 | 1 | 91.7% | 1 | 6 | 4 | January change load elevated but broadly controlled.
2026-02 | 42 | 18 | 20 | 4 | 39 | 2 | 1 | 92.9% | 1 | 7 | 5 | One emergency change caused minor user disruption.
2026-03 | 45 | 19 | 22 | 4 | 42 | 2 | 1 | 93.3% | 0 | 8 | 6 | Release quality improved after CAB tightening.
2026-04 | 39 | 17 | 19 | 3 | 37 | 1 | 1 | 94.9% | 0 | 6 | 5 | No major user impact from change activity.
2026-05 | 41 | 18 | 20 | 3 | 39 | 1 | 1 | 95.1% | 0 | 7 | 5 | Operational discipline remained good.
2026-06 | 44 | 19 | 21 | 4 | 42 | 1 | 1 | 95.5% | 0 | 9 | 7 | Strongest release month with controlled failure rate.

## INPUT_Dev_Delivery
INPUT Dev Delivery
One row per reporting month.
Reporting Month | Dev Tasks Opened | Dev Tasks Closed | Dev Backlog End | Average Dev Task Age Days | Oldest Open Dev Task Days | Blocked Items | Defects Delivered | Enhancements Delivered | Tech Debt Delivered | BAU Delivered | Dev CSAT / Sponsor Score | Commentary
2026-01 | 2 | 7 | 21 | 133 | 1027 | 5 | 2 | 2 | 1 | 2 | 4.3/5 | Backlog reduced but oldest item still distorting picture.
2026-02 | 5 | 2 | 24 | 146 | 1027 | 6 | 1 | 1 | 0 | 0 | 4.2/5 | Backlog reduction slowed; oldest items still need governance focus.
2026-03 | 7 | 5 | 26 | 141 | 1056 | 7 | 1 | 2 | 1 | 1 | 4.1/5 | New demand rose faster than throughput this month.
2026-04 | 9 | 11 | 23 | 128 | 1086 | 5 | 2 | 4 | 1 | 1 | 4.4/5 | Throughput improved after prioritisation reset.
2026-05 | 8 | 10 | 21 | 119 | 1117 | 4 | 2 | 3 | 2 | 1 | 4.5/5 | Backlog and age profile both improved.
2026-06 | 10 | 12 | 18 | 104 | 1147 | 3 | 3 | 4 | 2 | 1 | 4.6/5 | Best delivery month in the period with fewer blocked items.

## INPUT_Project_Portfolio
INPUT Project Portfolio
One row per project per reporting month.
Reporting Month | Project Name | Project Sponsor | Status RAG | Delivery Confidence % | Budget Status | Milestone Next | Milestone Date | Project CSAT | Benefits / Value Delivered | Blockers / Dependencies | Decision Needed? | Commentary
2026-01 | Estate Refresh Wave 2 | COO | Amber | 75% | Within budget | Roll-out complete | 2026-04-15 | 4.5/5 | Older kit retired in 4 branches | Supplier lead times | No | Execution underway with supply constraint.
2026-01 | Identity Modernisation | CEO | Green | 88% | Within budget | MFA finalisation | 2026-03-31 | 4.8/5 | Security uplift and lower admin overhead |  | No
2026-01 | Data & Reporting Uplift | CFO | Amber | 70% | Watch | Design sign-off | 2026-02-20 | 4.2/5 | Improved management information foundation | Business capacity | Yes | Need agreement on final scope.
2026-02 | Estate Refresh Wave 2 | COO | Amber | 75% | Within budget | Roll-out complete | 2026-04-15 | 4.5/5 | Older kit retired in 4 branches | Supplier lead times | No
2026-02 | Identity Modernisation | CEO | Green | 88% | Within budget | MFA finalisation | 2026-03-31 | 4.8/5 | Security uplift and lower admin overhead |  | No
2026-02 | Data & Reporting Uplift | CFO | Amber | 72% | Watch | Prototype review | 2026-03-18 | 4.3/5 | Better exec reporting structure | Competing priorities | Yes | Need design and data-model decision.
2026-03 | Estate Refresh Wave 2 | COO | Green | 84% | Within budget | Roll-out complete | 2026-04-15 | 4.6/5 | Reduced support drag in targeted branches |  | No | Supplier constraint eased.
2026-03 | Identity Modernisation | CEO | Green | 92% | Within budget | Hypercare exit | 2026-04-30 | 4.9/5 | Security and admin benefits realised |  | No
2026-03 | Data & Reporting Uplift | CFO | Amber | 74% | Watch | Design sign-off | 2026-04-12 | 4.4/5 | Clearer reporting vision agreed | Need ownership model | Yes
2026-04 | Estate Refresh Wave 2 | COO | Green | 95% | Within budget | Project closure | 2026-05-15 | 4.7/5 | Refresh completed in wave 2 scope |  | No
2026-04 | Identity Modernisation | CEO | Green | 95% | Within budget | Project closure | 2026-05-30 | 4.9/5 | Identity control uplift embedded |  | No
2026-04 | Data & Reporting Uplift | CFO | Amber | 76% | Within budget | Component design | 2026-05-20 | 4.4/5 | Reporting prototype progressed | Data readiness | Yes
2026-05 | Laptop Refresh Phase 3 | COO | Amber | 78% | Within budget | Mobilisation | 2026-06-21 | 4.4/5 | Next wave scoped and costed | Budget release | Yes | Needs funding confirmation.
2026-05 | Data & Reporting Uplift | CFO | Green | 82% | Within budget | Template pilot | 2026-06-18 | 4.5/5 | Core ingestion model in pilot | None | No
2026-05 | Security Remediation Sprint | CEO | Green | 86% | Within budget | Critical backlog clear-down | 2026-06-10 | 4.6/5 | Reduced high and critical exposure |  | No
2026-06 | Laptop Refresh Phase 3 | COO | Green | 85% | Within budget | Deployment start | 2026-07-15 | 4.5/5 | Q3 refresh ready to launch | Supplier delivery dates | No
2026-06 | Data & Reporting Uplift | CFO | Green | 88% | Within budget | Visual design pack | 2026-07-22 | 4.6/5 | Management reporting foundation established |  | No
2026-06 | Security Remediation Sprint | CEO | Green | 93% | Within budget | Closure and handover | 2026-07-05 | 4.7/5 | Material compliance improvement delivered |  | No

## INPUT_Rolling_Roadmap
INPUT Rolling Roadmap
One row per roadmap item. Use quarter labels and lanes. Keep to a rolling 4-quarter view.
Roadmap Quarter | Lane | Initiative | Status RAG | Outcome / Goal | Owner | Dependency | Decision Required | Notes
2026 Q2 | Infrastructure & cloud | WAN resilience uplift | Amber | Reduce single points of failure | Head of IT | Carrier lead time | No | Secondary path design agreed; implementation underway.
2026 Q2 | Security & compliance | Patch compliance uplift | Green | Meet critical patch target | Infrastructure Manager |  | No | Trajectory positive and on plan.
2026 Q2 | Applications & data | Exec reporting ingestion model | Amber | Standardise reporting inputs | IT Director | Data owner alignment | Yes | Agree ownership and sign-off model.
2026 Q3 | End-user computing | Laptop refresh phase 3 | Green | Reduce out-of-lifecycle estate | IT Operations | Budget approval | Yes | Spend envelope needed before bulk order.
2026 Q3 | Product / development | TABS prioritisation reset | Amber | Reduce oldest dev backlog | IT Director | Business prioritisation | Yes | Agree scope and sequencing.
2026 Q3 | Business transformation | Project portfolio governance refresh | Green | Improve prioritisation discipline | CIO |  | No | Steering cadence defined.
2026 Q4 | Security & compliance | Access control rationalisation | Amber | Reduce legacy permissions risk | Security Lead | Business testing windows | No | Cross-functional dependency to schedule.
2026 Q4 | Infrastructure & cloud | Private cloud rationalisation | Amber | Reduce hosted legacy risk | Head of IT | Commercial options review | Yes | Need decision on medium-term hosting target.
2026 Q4 | Applications & data | Management information self-service | Green | Improve reporting speed and consistency | Data Lead |  | No | Dependent on ingestion model maturation.
2027 Q1 | Core IT operations | Service desk workflow optimisation | Green | Cut avoidable handling effort | Service Desk Manager |  | No | Automation opportunities identified.
2027 Q1 | Product / development | Dev backlog quality reset | Amber | Retire stale demand and focus throughput | IT Director | Business sign-off | Yes | Need agreement on archive/close criteria.
2027 Q2 | Business transformation | Digital workplace enhancement | Green | Improve collaboration and productivity | CIO | Licensing decision | Yes | Dependent on M365 roadmap choice.

## INPUT_Gantt_Workstreams
INPUT Gantt Workstreams
One row per workstream per reporting month. Dates are rendered into the 12-week rolling Gantt.
Reporting Month | Workstream Name | Sponsor / Owner | Domain | Status RAG | Start Date | End Date | Progress Date | Detail / Commentary | Display Order | In Scope
2026-01 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2025-12-08 | 2026-02-15 | 2026-01-11 | Secondary path design agreed; implementation underway | 1 | Yes
2026-01 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-03-02 | 2026-05-24 |  | Commercial options review in progress | 2 | Yes
2026-01 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2025-12-22 | 2026-02-15 | 2026-01-11 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-01 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-02-16 | 2026-03-29 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-01 | Security Remediation Sprint | CEO | Security & compliance | Green | 2025-11-24 | 2026-01-18 | 2026-01-11 | Critical backlog cleared; wrapping up | 5 | Yes
2026-01 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-03-16 | 2026-05-24 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-01 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2025-11-10 | 2026-02-01 | 2026-01-11 | Continuous programme; trajectory positive | 7 | Yes
2026-01 | Data & Reporting Uplift | CFO | Applications & data | Green | 2025-10-27 | 2026-02-01 | 2026-01-11 | Management reporting foundation established | 8 | Yes
2026-01 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-03-30 | 2026-06-07 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-01 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-01-19 | 2026-03-15 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-01 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-04-13 | 2026-06-07 |  | Archive and close criteria decision pending | 11 | Yes
2026-01 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2025-12-22 | 2026-02-01 | 2026-01-04 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-01 | Identity Modernisation | CEO | Business transformation | Green | 2025-09-15 | 2026-01-04 | 2025-12-28 | Security uplift and admin overhead reduction delivered | 13 | Yes
2026-02 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2026-01-05 | 2026-03-15 | 2026-02-08 | Secondary path design agreed; implementation underway | 1 | Yes
2026-02 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-03-30 | 2026-06-21 |  | Commercial options review in progress | 2 | Yes
2026-02 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2026-01-19 | 2026-03-15 | 2026-02-08 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-02 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-03-16 | 2026-04-26 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-02 | Security Remediation Sprint | CEO | Security & compliance | Green | 2025-12-22 | 2026-02-15 | 2026-02-08 | Critical backlog cleared; wrapping up | 5 | Yes
2026-02 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-04-13 | 2026-06-21 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-02 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2025-12-08 | 2026-03-01 | 2026-02-08 | Continuous programme; trajectory positive | 7 | Yes
2026-02 | Data & Reporting Uplift | CFO | Applications & data | Green | 2025-11-24 | 2026-03-01 | 2026-02-08 | Management reporting foundation established | 8 | Yes
2026-02 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-04-27 | 2026-07-05 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-02 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-02-16 | 2026-04-12 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-02 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-05-11 | 2026-07-05 |  | Archive and close criteria decision pending | 11 | Yes
2026-02 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2026-01-19 | 2026-03-01 | 2026-02-01 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-02 | Identity Modernisation | CEO | Business transformation | Green | 2025-10-13 | 2026-02-01 | 2026-01-25 | Security uplift and admin overhead reduction delivered | 13 | Yes
2026-03 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2026-02-02 | 2026-04-12 | 2026-03-08 | Secondary path design agreed; implementation underway | 1 | Yes
2026-03 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-04-27 | 2026-07-19 |  | Commercial options review in progress | 2 | Yes
2026-03 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2026-02-16 | 2026-04-12 | 2026-03-08 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-03 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-04-13 | 2026-05-24 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-03 | Security Remediation Sprint | CEO | Security & compliance | Green | 2026-01-19 | 2026-03-15 | 2026-03-08 | Critical backlog cleared; wrapping up | 5 | Yes
2026-03 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-05-11 | 2026-07-19 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-03 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2026-01-05 | 2026-03-29 | 2026-03-08 | Continuous programme; trajectory positive | 7 | Yes
2026-03 | Data & Reporting Uplift | CFO | Applications & data | Green | 2025-12-22 | 2026-03-29 | 2026-03-08 | Management reporting foundation established | 8 | Yes
2026-03 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-05-25 | 2026-08-02 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-03 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-03-16 | 2026-05-10 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-03 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-06-08 | 2026-08-02 |  | Archive and close criteria decision pending | 11 | Yes
2026-03 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2026-02-16 | 2026-03-29 | 2026-03-01 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-03 | Identity Modernisation | CEO | Business transformation | Green | 2025-11-10 | 2026-03-01 | 2026-02-22 | Security uplift and admin overhead reduction delivered | 13 | Yes
2026-04 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2026-03-09 | 2026-05-17 | 2026-04-12 | Secondary path design agreed; implementation underway | 1 | Yes
2026-04 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-06-01 | 2026-08-23 |  | Commercial options review in progress | 2 | Yes
2026-04 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2026-03-23 | 2026-05-17 | 2026-04-12 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-04 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-05-18 | 2026-06-28 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-04 | Security Remediation Sprint | CEO | Security & compliance | Green | 2026-02-23 | 2026-04-19 | 2026-04-12 | Critical backlog cleared; wrapping up | 5 | Yes
2026-04 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-06-15 | 2026-08-23 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-04 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2026-02-09 | 2026-05-03 | 2026-04-12 | Continuous programme; trajectory positive | 7 | Yes
2026-04 | Data & Reporting Uplift | CFO | Applications & data | Green | 2026-01-26 | 2026-05-03 | 2026-04-12 | Management reporting foundation established | 8 | Yes
2026-04 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-06-29 | 2026-09-06 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-04 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-04-20 | 2026-06-14 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-04 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-07-13 | 2026-09-06 |  | Archive and close criteria decision pending | 11 | Yes
2026-04 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2026-03-23 | 2026-05-03 | 2026-04-05 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-04 | Identity Modernisation | CEO | Business transformation | Green | 2025-12-15 | 2026-04-05 | 2026-03-29 | Security uplift and admin overhead reduction delivered | 13 | Yes
2026-05 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2026-04-06 | 2026-06-14 | 2026-05-10 | Secondary path design agreed; implementation underway | 1 | Yes
2026-05 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-06-29 | 2026-09-20 |  | Commercial options review in progress | 2 | Yes
2026-05 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2026-04-20 | 2026-06-14 | 2026-05-10 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-05 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-06-15 | 2026-07-26 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-05 | Security Remediation Sprint | CEO | Security & compliance | Green | 2026-03-23 | 2026-05-17 | 2026-05-10 | Critical backlog cleared; wrapping up | 5 | Yes
2026-05 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-07-13 | 2026-09-20 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-05 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2026-03-09 | 2026-05-31 | 2026-05-10 | Continuous programme; trajectory positive | 7 | Yes
2026-05 | Data & Reporting Uplift | CFO | Applications & data | Green | 2026-02-23 | 2026-05-31 | 2026-05-10 | Management reporting foundation established | 8 | Yes
2026-05 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-07-27 | 2026-10-04 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-05 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-05-18 | 2026-07-12 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-05 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-08-10 | 2026-10-04 |  | Archive and close criteria decision pending | 11 | Yes
2026-05 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2026-04-20 | 2026-05-31 | 2026-05-03 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-05 | Identity Modernisation | CEO | Business transformation | Green | 2026-01-12 | 2026-05-03 | 2026-04-26 | Security uplift and admin overhead reduction delivered | 13 | Yes
2026-06 | WAN Resilience Uplift | Head of IT | Infrastructure | Amber | 2026-05-04 | 2026-07-12 | 2026-06-07 | Secondary path design agreed; implementation underway | 1 | Yes
2026-06 | Private Cloud Rationalisation | Head of IT | Infrastructure | Amber | 2026-07-27 | 2026-10-18 |  | Commercial options review in progress | 2 | Yes
2026-06 | Laptop Refresh Phase 3 | COO | End-user computing | Green | 2026-05-18 | 2026-07-12 | 2026-06-07 | Q3 refresh ready to launch; supplier slots confirmed | 3 | Yes
2026-06 | Mobile Fleet Review | IT Operations | End-user computing | Green | 2026-07-13 | 2026-08-23 |  | Scheduled for Q3; estate in good health | 4 | Yes
2026-06 | Security Remediation Sprint | CEO | Security & compliance | Green | 2026-04-20 | 2026-06-14 | 2026-06-07 | Critical backlog cleared; wrapping up | 5 | Yes
2026-06 | Access Control Rationalisation | Security Lead | Security & compliance | Amber | 2026-08-10 | 2026-10-18 |  | Cross-functional dependency; scheduling in progress | 6 | Yes
2026-06 | Patch Compliance Uplift | Infrastructure Manager | Security & compliance | Green | 2026-04-06 | 2026-06-28 | 2026-06-07 | Continuous programme; trajectory positive | 7 | Yes
2026-06 | Data & Reporting Uplift | CFO | Applications & data | Green | 2026-03-23 | 2026-06-28 | 2026-06-07 | Management reporting foundation established | 8 | Yes
2026-06 | MI Self-Service Reporting | Data Lead | Applications & data | Green | 2026-08-24 | 2026-11-01 |  | Dependent on ingestion model; planned Q4 | 9 | Yes
2026-06 | TABS Prioritisation Reset | IT Director | Product / development | Amber | 2026-06-15 | 2026-08-09 |  | Business prioritisation required before mobilisation | 10 | Yes
2026-06 | Dev Backlog Quality Reset | IT Director | Product / development | Amber | 2026-09-07 | 2026-11-01 |  | Archive and close criteria decision pending | 11 | Yes
2026-06 | Portfolio Governance Refresh | CIO | Business transformation | Green | 2026-05-18 | 2026-06-28 | 2026-05-31 | Prioritisation discipline; steering cadence defined | 12 | Yes
2026-06 | Identity Modernisation | CEO | Business transformation | Green | 2026-02-09 | 2026-05-31 | 2026-05-24 | Security uplift and admin overhead reduction delivered | 13 | Yes

## INPUT_Gantt_Milestones
INPUT Gantt Milestones
Child milestone rows for the Portfolio Gantt. Multiple milestones per workstream are supported.
Reporting Month | Workstream Name | Milestone Label | Milestone Date | Display Order
2026-01 | WAN Resilience Uplift | Secondary path live | 2026-01-19 | 1
2026-01 | Private Cloud Rationalisation | Options decision | 2026-05-25 | 2
2026-01 | Laptop Refresh Phase 3 | Deployment start | 2026-01-05 | 3
2026-01 | Security Remediation Sprint | Closure & handover | 2025-12-08 | 4
2026-01 | Data & Reporting Uplift | Visual design pack | 2025-11-17 | 5
2026-01 | TABS Prioritisation Reset | Scope agreed | 2026-02-16 | 6
2026-01 | Portfolio Governance Refresh | Steering cadence | 2026-01-19 | 7
2026-01 | Identity Modernisation | Project closure | 2025-09-22 | 8
2026-02 | WAN Resilience Uplift | Secondary path live | 2026-02-16 | 1
2026-02 | Private Cloud Rationalisation | Options decision | 2026-06-22 | 2
2026-02 | Laptop Refresh Phase 3 | Deployment start | 2026-02-02 | 3
2026-02 | Security Remediation Sprint | Closure & handover | 2026-01-05 | 4
2026-02 | Data & Reporting Uplift | Visual design pack | 2025-12-15 | 5
2026-02 | TABS Prioritisation Reset | Scope agreed | 2026-03-16 | 6
2026-02 | Portfolio Governance Refresh | Steering cadence | 2026-02-16 | 7
2026-02 | Identity Modernisation | Project closure | 2025-10-20 | 8
2026-03 | WAN Resilience Uplift | Secondary path live | 2026-03-16 | 1
2026-03 | Private Cloud Rationalisation | Options decision | 2026-07-20 | 2
2026-03 | Laptop Refresh Phase 3 | Deployment start | 2026-03-02 | 3
2026-03 | Security Remediation Sprint | Closure & handover | 2026-02-02 | 4
2026-03 | Data & Reporting Uplift | Visual design pack | 2026-01-12 | 5
2026-03 | TABS Prioritisation Reset | Scope agreed | 2026-04-13 | 6
2026-03 | Portfolio Governance Refresh | Steering cadence | 2026-03-16 | 7
2026-03 | Identity Modernisation | Project closure | 2025-11-17 | 8
2026-04 | WAN Resilience Uplift | Secondary path live | 2026-04-20 | 1
2026-04 | Private Cloud Rationalisation | Options decision | 2026-08-24 | 2
2026-04 | Laptop Refresh Phase 3 | Deployment start | 2026-04-06 | 3
2026-04 | Security Remediation Sprint | Closure & handover | 2026-03-09 | 4
2026-04 | Data & Reporting Uplift | Visual design pack | 2026-02-16 | 5
2026-04 | TABS Prioritisation Reset | Scope agreed | 2026-05-18 | 6
2026-04 | Portfolio Governance Refresh | Steering cadence | 2026-04-20 | 7
2026-04 | Identity Modernisation | Project closure | 2025-12-22 | 8
2026-05 | WAN Resilience Uplift | Secondary path live | 2026-05-18 | 1
2026-05 | Private Cloud Rationalisation | Options decision | 2026-09-21 | 2
2026-05 | Laptop Refresh Phase 3 | Deployment start | 2026-05-04 | 3
2026-05 | Security Remediation Sprint | Closure & handover | 2026-04-06 | 4
2026-05 | Data & Reporting Uplift | Visual design pack | 2026-03-16 | 5
2026-05 | TABS Prioritisation Reset | Scope agreed | 2026-06-15 | 6
2026-05 | Portfolio Governance Refresh | Steering cadence | 2026-05-18 | 7
2026-05 | Identity Modernisation | Project closure | 2026-01-19 | 8
2026-06 | WAN Resilience Uplift | Secondary path live | 2026-06-15 | 1
2026-06 | Private Cloud Rationalisation | Options decision | 2026-10-19 | 2
2026-06 | Laptop Refresh Phase 3 | Deployment start | 2026-06-01 | 3
2026-06 | Security Remediation Sprint | Closure & handover | 2026-05-04 | 4
2026-06 | Data & Reporting Uplift | Visual design pack | 2026-04-13 | 5
2026-06 | TABS Prioritisation Reset | Scope agreed | 2026-07-13 | 6
2026-06 | Portfolio Governance Refresh | Steering cadence | 2026-06-15 | 7
2026-06 | Identity Modernisation | Project closure | 2026-02-16 | 8

## INPUT_Budget_Commercials
INPUT Budget Commercials
One row per budget line per reporting month. Add renewals as separate rows using the Renewal Due Date fields.
Reporting Month | Budget Line | Budget Amount | Actual Amount | Forecast Amount | Variance | Cloud / Licensing Spend | Asset Refresh Spend | Savings Achieved | Avoidable Cost Risk | Vendor / Contract | Renewal Due Date | Renewal Value | Owner | Commentary
2026-01 | Cloud services | 25000 | 24620 | 24800 | -380 | 24620 | 0 | 0 | 900 | AWS Support | 2026-06-30 | 18000 | CIO | Spend broadly on plan.
2026-01 | Licensing | 41000 | 41980 | 42200 | 980 | 41980 | 0 | 300 | 2200 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Slight licence growth pressure emerging.
2026-01 | Hardware / refresh | 20000 | 14200 | 19500 | -5800 | 0 | 14200 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops | Refresh spend behind profile due to supply timing.
2026-01 | Connectivity | 14000 | 14120 | 14100 | 120 | 0 | 0 | 0 | 500 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT | Carrier costs slightly above budget.
2026-02 | Cloud services | 25000 | 23850 | 24800 | -1150 | 23850 | 0 | 0 | 900 | AWS Support | 2026-06-30 | 18000 | CIO | Spend under budget this month.
2026-02 | Licensing | 41000 | 42150 | 42400 | 1150 | 42150 | 0 | 500 | 2500 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Slight overspend from licence growth.
2026-02 | Hardware / refresh | 20000 | 18500 | 19600 | -1500 | 0 | 18500 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops | Refresh spend tracking to plan.
2026-02 | Connectivity | 14000 | 13960 | 14050 | -40 | 0 | 0 | 0 | 500 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT | Connectivity stable and near budget.
2026-03 | Cloud services | 25000 | 24120 | 24700 | -880 | 24120 | 0 | 0 | 850 | AWS Support | 2026-06-30 | 18000 | CIO
2026-03 | Licensing | 41000 | 42340 | 42500 | 1340 | 42340 | 0 | 700 | 2500 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Optimisation action identified.
2026-03 | Hardware / refresh | 20000 | 12400 | 18700 | -7600 | 0 | 12400 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops | Spend timing deferred into Q2.
2026-03 | Connectivity | 14000 | 13880 | 13990 | -120 | 0 | 0 | 0 | 500 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT
2026-04 | Cloud services | 25000 | 23940 | 24600 | -1060 | 23940 | 0 | 0 | 800 | AWS Support | 2026-06-30 | 18000 | CIO
2026-04 | Licensing | 41000 | 41890 | 42100 | 890 | 41890 | 0 | 900 | 2100 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Optimisation starting to land.
2026-04 | Hardware / refresh | 20000 | 15600 | 19800 | -4400 | 0 | 15600 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops
2026-04 | Connectivity | 14000 | 13910 | 13980 | -90 | 0 | 0 | 0 | 400 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT
2026-05 | Cloud services | 25000 | 24280 | 24750 | -720 | 24280 | 0 | 150 | 700 | AWS Support | 2026-06-30 | 18000 | CIO | Usage stable.
2026-05 | Licensing | 41000 | 41520 | 41800 | 520 | 41520 | 0 | 1200 | 1800 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Savings from licence clean-up beginning to show.
2026-05 | Hardware / refresh | 20000 | 9200 | 18100 | -10800 | 0 | 9200 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops | Q3 ordering not yet started.
2026-05 | Connectivity | 14000 | 13870 | 13920 | -130 | 0 | 0 | 0 | 400 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT
2026-06 | Cloud services | 25000 | 24410 | 24800 | -590 | 24410 | 0 | 200 | 650 | AWS Support | 2026-06-30 | 18000 | CIO | Renewal prep under way.
2026-06 | Licensing | 41000 | 41280 | 41600 | 280 | 41280 | 0 | 1500 | 1600 | Microsoft EA / CSP | 2026-11-30 | 510000 | CIO | Best variance in the half-year.
2026-06 | Hardware / refresh | 20000 | 11800 | 18950 | -8200 | 0 | 11800 | 0 | 0 | HP Device Refresh | 2026-09-15 | 76000 | IT Ops | Budget held for Q3 wave mobilisation.
2026-06 | Connectivity | 14000 | 13840 | 13900 | -160 | 0 | 0 | 0 | 350 | WAN / ISP Services | 2026-08-31 | 168000 | Head of IT

## INPUT_Top_Risks
INPUT Top Risks
One row per risk or issue. Keep this to the top items only.
Reporting Month | Risk / Issue | Type | Owner | Impact | Likelihood | Rating RAG | Current Control / Mitigation | Target Date | Decision Required? | Commentary
2026-06 | Ageing laptop estate could still drive avoidable incidents if Q3 refresh slips | Operational | IT Operations | High | Likely | Amber | Prepare order and protect budget envelope | 2026-07-15 | Yes | Needs timely funding and supplier slot.
2026-06 | Microsoft renewal remains a material H2 commercial event | Commercial | CIO | High | Possible | Amber | Early market engagement and optimisation work | 2026-09-30 | Yes | Decision needed on commercial route and term.
2026-06 | Historic development backlog may continue to distort confidence and stakeholder trust | Delivery | IT Director | High | Likely | Amber | Prioritisation reset and stale-item governance | 2026-08-31 | Yes | Requires business sponsorship and close criteria.
2026-06 | Private cloud remains a residual resilience concern despite recent improvement | Operational | Head of IT | Medium | Possible | Amber | Monitor, harden and review rationalisation options | 2026-10-31 | No | Improved but still not target-state.
2026-06 | Data ownership inconsistency could slow exec reporting maturity | Governance | CIO | Medium | Likely | Amber | Define named data owners by domain | 2026-07-31 | Yes | Needed for sustainable reporting process.
2026-06 | Patch compliance could regress if operational capacity is diverted into project work | Security | Infrastructure Manager | Medium | Possible | Green | Maintain monthly patch cadence and reporting | 2026-09-30 | No | Currently stable but capacity-sensitive.

## INPUT_Narrative_Notes
INPUT Narrative Notes
One row per page / section. Use this for curated commentary, wins, concerns and decisions rather than letting commentary drift across tabs.
Reporting Month | Section | Note Type | Headline | Narrative | Owner
2026-06 | Executive scorecard | Win | Core service availability strongest in the half-year | June delivered excellent availability across network, cloud and critical platforms with no major incidents. | Head of IT
2026-06 | Support operations and user experience | Win | Support performance improved while ticket CSAT remained high | Average resolution time reduced to 1.2 days and CSAT improved to 4.8/5. | Service Desk Manager
2026-06 | Security, patching and compliance | Win | Critical vulnerability backlog reduced to zero | Patch compliance and remediation controls are now materially stronger than at the start of the year. | Infrastructure Manager
2026-06 | Estate, assets and lifecycle | Concern | Refresh progress still depends on protected Q3 funding | Lifecycle health has improved, but progress will stall without the next refresh wave. | IT Operations
2026-06 | Budget and commercials | Concern | Licensing remains the main commercial pressure line | The position is improving, but optimisation work must continue before renewal. | CIO
2026-06 | Top risks and decisions | Decision needed | Approve Q3 device refresh spend envelope | Approving the refresh envelope now protects supplier lead times and supports further reduction in aged-estate incidents. | CIO
2026-06 | Delivery, projects and rolling roadmap | Win | Delivery confidence is improving across the active portfolio | Project CSAT and delivery confidence both improved after governance tightening. | IT Director

## INPUT_Chart_Settings
INPUT Chart Settings
Optional chart overlays and thresholds. One row per chart per reporting month.
Reporting Month | Page | Chart Key | Overlay Enabled | Overlay Metric | Rolling Window | Healthy Min | Amber Min | Commentary
2026-01 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.
2026-02 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.
2026-03 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.
2026-04 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.
2026-05 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.
2026-06 | Support Operations | support_ticket_volumes | Yes | Close Balance % | 3 | 100 | 97 | Overlay highlights whether ticket closures are keeping pace with incoming demand.